## Slide 1: Facilities Update
Presented to:
Garden Grove Unified School District
Bond Oversight Committee
May 8, 2018
Presented by: Jerry Hills & Kevin Heerschap

## Slide 2
Measure A: Project List
Completed, Under Construction
Elementary
  Basic Modernization: Completed at 34 schools
  Modernization & HVAC/Ancillary Improvements: 13 schools
Intermediate
  Modernization & HVAC and Ancillary Improvements: 9 schools
  Basic Modernization: 2 Schools. Bell & Jordan ATP (Existing AC)
High School
  Modernization & HVAC/Ancillary Improvements : 5 schools
    Bolsa, Grove, Santiago, Rancho, Los Amigos
  Modernization & HVAC/Ancillary Improvements: LQ/Pacifica Admin and Industrial Arts Buildings
  Modernization: Santiago(HVAC/Ancillary Improvements under “P”)
Measure P Planning
  Seismic & HVAC design

## Slide 3
Measure P: Project List
Completed, Under Construction, Future
Santiago HS HVAC/Ancillary Improvements
Seismic (Pacifica/La Quinta)
Athletics Stadium Upgrades(GGHS/BGHS)
Gyms/Locker Rooms (La Quinta/Pacifica)
Elementary HVAC/Ancillary Improvements (25 schools)
Roofing (19 schools)
Electrical Switchgear Replacement (11 schools)
HVAC and Insulation Improvements (13 schools, Edgar, DO)

## Slide 4
    HVAC
    Seismic Replacements
      Classrooms/Gyms
    Stadium Renovation
    Projects
      Completed, Under Construction, Future
Measure P Overview

## Slide 5
5 Projects completed summer 2017
19 future elementary projects
  All 19 projects have been awarded
  2018: 7 Schools - Bryant, Parkview, Simmons, Violette, Warren, Woodbury, Garden Park
  2019: 6 Schools TBD
  2020: 6 Schools TBD
Elementary HVAC Projects

## Slide 6: Seismic Replacement
  LQ/Pacifica Classroom Buildings
  LQ/Pacifica Gym Locker Buildings

## Slide 7
Seismic Replacement
Phase 1- Start June 2016, construction of 32 Classrooms/
Demo of existing CR building -Completion September 2017
Phase 2- Start June 2017, Construction of 32 Classrooms and Cafeteria/ Demo of existing CR and Cafeteria Building
-Completion August 2018 Phase 3- Start June 2018, Construction of Media Center and Theater -Completion – December 2019
PACIFICA/LA QUINTA HIGH SCHOOL BUILDINGS

## Slide 8
Pacifica HS
New Building Corridors with Seat walls
Seismic Replacement

## Slide 9
Pacifica HS
New Cafeteria Front
Seismic Replacement

## Slide 10
Pacifica HS
New Cafeteria Staff Dining Area
Seismic Replacement

## Slide 11
La Quinta HS
New Building Corridors with Seat walls
Seismic Replacement

## Slide 12
La Quinta HS
New Cafeteria Front
Seismic Replacement

## Slide 13
La Quinta HS
New Cafeteria Staff Dining Area
Seismic Replacement

## Slide 14
Seismic Replacement
Seismic Gym Locker Buildings
  Pacifica and LQ
  DSA Approved in September 2017
  Gymnasium, Locker Rooms, Pool
  Approved for Partial State Funding
  Anticipated Construction Start 2019

## Slide 15
Pacifica/LQ gym locker

## Slide 16
Michael A. Monsoor
Memorial Stadium
(Completed September 2017)
Bolsa Stadium
(Construction to begin Winter 2018)
Stadium Renovations

## Slide 17
Garden Grove HS
Completed September 2017
Monsoor Stadium

## Slide 18
Bolsa Stadium Schedule
Currently in design
Plans will be submitted to DSA June 2018
Proposals to be received October 2018
Anticipated award November 2018
Construction begins December 2018
(as soon as football is over)

## Slide 19
Proposed Layout
Bolsa Stadium

## Slide 20
Project List
Completed, Under Construction, Future
Santiago HS HVAC
Seismic (Pacifica/La Quinta)
Athletics Stadium Upgrades(GGHS/BGHS)
Gyms/Locker Rooms (La Quinta/Pacifica)
Elementary HVAC (25 SCHOOLS)
Roofing (19 SCHOOLS)
Security, Fencing, Intrusion Alarms
HS Gym Floor/Bleachers (SHS, RAHS, GGHS, LAHS, BGHS)
HS Pool Renovations(SHS, LAHS, BGHS, RAHS)
Don Wash Auditorium
Resurface Tennis Courts (All HS)
Varsity Baseball Dugouts (All HS)
Total estimated cost $375,300,500

## Slide 21
Bolsa Building R
  Contract has been issued
  Scheduled to begin June 2018
  Completion 2019
Under Construction

## Slide 22
Under Construction
Ralston IS
Typical Classroom Interior
Casework, Flooring, Dropped Ceiling, LED Lights, Energy Efficient Windows

## Slide 23
Under Construction
Bolsa Grande
ASB Store
Energy efficient windows, Accessible Doors,
ADA Path of Travel

## Slide 24
Under Construction
Bolsa Grande
New Science Room Interior
Casework, Gas, Plumbing, Flooring, LED Lights, Energy Efficient Windows

## Slide 25
Under Construction
Los Amigos HS
Typical Classroom Interior
Flooring, Dropped Ceiling, LED Lights, Teaching Wall Short Throw Projector, Atlas Clock

## Slide 26
Under Construction
Santiago HS
Phase 4
New AC units
Roofing getting ready to be Made water tight

## Slide 27
Under Construction
Santiago HS
Phase 4
Pouring Concrete For New Accessible Pathway

## Slide 28
QUESTIONS

## Slide 29
Facilities Update
Thank You!